## Read me
Northbridge Supplies: UAT test plan
What this is | User acceptance testing (UAT) for the new invoice approval process. Real users test it before go-live, to confirm it works the way the requirements say. Each test case comes from an acceptance criterion in the requirements spreadsheet.
Author | Felicia Oyebode, Business Analyst
In scope | Phase A and Phase B stories (US01 to US10, and US12). Phase C (US11) will be tested in its own project. Won't-have stories (US13, US14) are not tested.
How to use it | Testers fill in the yellow columns on the Test cases tab: the date tested, Pass / Fail / Blocked, what actually happened, and any defect number. The Summary tab updates by itself.
Ready to start testing when
1 | The workflow module is set up in a test copy of the finance system
2 | The approval list and backup approvers are loaded
3 | Testers have had a short walkthrough
Ready to go live when
1 | Every Must-have test has passed
2 | No open high-priority defects
3 | Helen Marsh signs off
Testers | AP clerk, AP team lead (Daniel Okafor), Operations Manager (Mark Reid), Marketing Manager, Operations supervisor, Procurement lead, Financial Controller, Finance Director (Helen Marsh), Finance owner
Note | Test data uses real examples from the 2025 invoice data where useful. Northbridge Supplies is a fictional company. This is a portfolio case study.

## Test cases
Test ID | Story | What we're testing | Steps | Test data | Expected result | Tester | Date tested | Result | What actually happened | Defect ref
TC01 | US01 | Exact duplicate is blocked | 1. Log an invoice from Albion Packaging Ltd with invoice number 001-13797. 2. Log the same invoice again. | Albion Packaging Ltd, 001-13797, £1,979.70 (one of the 2025 duplicates) | Second invoice is blocked from payment. AP gets an alert with a link to the first one. | AP clerk |  | Not run
TC02 | US01 | Near-duplicate with different punctuation is blocked | 1. Log invoice 004-10261 from Dunmore Packaging Ltd. 2. Log the same invoice with the number typed as 004 10261. | Dunmore Packaging Ltd, 004-10261, £310.42 | Second invoice is treated as a duplicate and blocked. | AP clerk |  | Not run
TC03 | US01 | Only the Financial Controller can release a blocked invoice | 1. As an AP clerk, try to release a blocked invoice. 2. As the Financial Controller, release it without a reason. 3. Release it again, this time with a reason. | Any blocked invoice from the tests above | AP clerk cannot release it. Financial Controller cannot release it without a reason. With a reason, it is released and the reason is saved. | AP clerk, Financial Controller |  | Not run
TC04 | US01 | Different invoice from the same supplier is not blocked | 1. Log a new invoice from Albion Packaging Ltd with a different invoice number. | Albion Packaging Ltd, new invoice number | Invoice is accepted as normal. No duplicate alert. | AP clerk |  | Not run
TC05 | US02 | Duplicate payments list is complete | 1. Open the list of 2025 duplicate payments. 2. Add up the amounts and count the lines. | 2025 duplicates list | List shows supplier, invoice number, amount and both payment dates. 45 invoices totalling £158,776. | Financial Controller |  | Not run
TC06 | US02 | Recovery status can be tracked | 1. Pick one line on the list. 2. Change its status to 'Requested', then 'Agreed', then 'Received'. | Any line on the list | Each status saves and shows on the list. | Financial Controller |  | Not run
TC07 | US03 | Invoice with no PO is returned to the supplier | 1. Log an invoice with no PO number. 2. Return it using the standard email. | Test invoice with blank PO field | Standard email goes to the supplier within 1 working day. Invoice shows as 'returned: no PO'. | AP clerk |  | Not run
TC08 | US03 | Resent invoice with a valid PO goes through normally | 1. Log the returned invoice again, now with a valid PO number. | Same supplier and amount, valid PO added | Invoice goes through the normal process. It is not flagged as a duplicate of the returned one. | AP clerk |  | Not run
TC09 | US04 | Emergency PO can be raised quickly on a phone | 1. On a phone, open the emergency PO form. 2. Enter supplier, description, rough cost and cost centre. 3. Submit and time it. | Forklift repair, about £850, Operations cost centre | Only those four fields are needed. A PO number appears straight away. Takes under 2 minutes. | Operations supervisor |  | Not run
TC10 | US04 | Budget holder is told about the emergency PO | 1. Raise an emergency PO as above. 2. Check the budget holder's notifications. | As above | Budget holder is notified with the PO details. | Operations Manager |  | Not run
TC11 | US04 | Monthly list of emergency POs is produced | 1. Raise three emergency POs during the test period. 2. Run the month-end emergency PO list. | Three test emergency POs | All three appear on the list with who raised them, supplier and amount. | Financial Controller |  | Not run
TC12 | US05 | Supplier notice reaches all regular suppliers | 1. Get the list of suppliers invoiced in the last 12 months. 2. Check it against the list the notice was sent to. | Supplier list and notice mailing list | Every supplier on the 12-month list received the notice. Notice names a Procurement contact. | Procurement lead |  | Not run
TC13 | US06 | Matched invoice goes to the right approver | 1. Log a matched invoice for the Marketing department under £10,000. 2. Time how long it takes to reach the approver. | Marketing invoice, £2,400, matched to PO | Goes to the Marketing Manager within 5 minutes. | AP clerk |  | Not run
TC14 | US06 | Invoice of £10,000 or more goes to the Finance Director next | 1. Log a matched invoice of £12,000. 2. Approve it as the budget holder. | Operations invoice, £12,000, matched to PO | After the budget holder approves, it goes to the Finance Director automatically. | Operations Manager, Finance Director |  | Not run
TC15 | US06 | Invoice at exactly £10,000 needs a second approval | 1. Log a matched invoice of exactly £10,000.00. 2. Approve it as the budget holder. | Any department, £10,000.00 | Goes to the Finance Director after the budget holder. (Checks the boundary: 'or over' includes £10,000.) | AP clerk |  | Not run
TC16 | US06 | Invoice with no approver set up goes to the AP queue | 1. Log a matched invoice for a test department with no approver. | Test department with no approver | Invoice goes to the AP queue and AP gets an alert. | AP clerk |  | Not run
TC17 | US07 | Approver gets a phone notification | 1. Send a matched invoice for approval. 2. Check the approver's phone. | Operations invoice, £1,500 | Notification arrives within 5 minutes. | Operations Manager |  | Not run
TC18 | US07 | PO details show next to the invoice | 1. Open the invoice from the notification. | As above | PO number, amount and supplier are shown next to the invoice. | Operations Manager |  | Not run
TC19 | US07 | Rejecting needs a reason | 1. Try to reject the invoice without a reason. 2. Reject it with a reason. | As above | Can't reject without a reason. With a reason, it is rejected and AP can see why. | Operations Manager |  | Not run
TC20 | US08 | Reminder after 3 working days | 1. Send an invoice for approval and take no action. 2. Move the test clock forward 3 working days. | Any routed invoice | Approver gets a reminder. It shows in the invoice history with the date. | AP clerk |  | Not run
TC21 | US08 | Escalation after 5 working days | 1. Leave the same invoice with no action. 2. Move the test clock forward to 5 working days. | As above | Invoice goes to the backup approver. AP is told. | AP clerk |  | Not run
TC22 | US08 | Weekends don't count towards the limit | 1. Send an invoice for approval on a Friday. 2. Check on Monday and on Wednesday. | Any routed invoice | No reminder on Monday. Reminder on Wednesday (3 working days). | AP clerk |  | Not run
TC23 | US09 | Backup approver is required | 1. Try to add a new budget holder without a backup. | Test budget holder | System won't save without a backup approver. | Finance owner |  | Not run
TC24 | US09 | Invoices go to the backup when someone is away | 1. Mark the Marketing Manager as away. 2. Send a Marketing invoice for approval. 3. Approve it as the backup. | Marketing invoice, £800 | Goes straight to the backup. The record shows who approved it and that they were covering. | Marketing Manager's backup |  | Not run
TC25 | US10 | Query needs an owner, reason and due date | 1. Raise a query on a price mismatch invoice. 2. Try to save it with no owner. | Invoice with price mismatch | Can't save without owner, reason and due date. | AP team lead |  | Not run
TC26 | US10 | Overdue queries are highlighted | 1. Raise a query with a due date of yesterday. 2. Open the AP query list. | As above | Overdue query is highlighted. | AP team lead |  | Not run
TC27 | US10 | Closing a query needs a resolution note | 1. Try to close a query without a note. 2. Close it with a note. | As above | Can't close without a note. With a note, it closes. | AP team lead |  | Not run
TC28 | US12 | On-time % shows against the 95% target | 1. Open the dashboard after month-end. | Test month's data | Shows % paid on time with the 95% target line. Figure matches a manual count. | Finance Director |  | Not run
TC29 | US12 | Approval days by approver | 1. Open the approvals view. | Test month's data | Average approval days shows for each approver. One approver's figure matches a manual check. | Finance Director |  | Not run
TC30 | US12 | Controls figures are shown | 1. Open the controls view. | Test month's data | Shows duplicates blocked, invoices returned for no PO, and open queries. Each matches the test log. | Finance Director |  | Not run

## Summary
Test progress
Result | Test cases | Share
Pass | 0 | 0%
Fail | 0 | 0%
Blocked | 0 | 0%
Not run | 30 | 100%
Total | 30 | 100%
Ready to go live? | Not yet
Rule: every test passed, none failed, blocked or not run, and no open high-priority defects.
By story
Story | Test cases | Passed | Failed
US01 | 4 | 0 | 0
US02 | 2 | 0 | 0
US03 | 2 | 0 | 0
US04 | 3 | 0 | 0
US05 | 1 | 0 | 0
US06 | 4 | 0 | 0
US07 | 3 | 0 | 0
US08 | 3 | 0 | 0
US09 | 2 | 0 | 0
US10 | 3 | 0 | 0
US12 | 3 | 0 | 0